## Blad1
AVG. Team Speed | 30 |  |  |  |  | Total: | 35.2 | Sprints
Prio | Epic names | Features | Number of User Stories so far | Estimation (Architect View) | Estimation (Second Expert) | Current Progress (%) | Predicted number of Sprints to Deliver ( 1 Sprint = avg Team spead in SP - C1 ) | The Size
1 | WebCon 2017 | Features so Far - based on Jira | 50 | 84.4 | 84.4 | 23.6 | 9.2 | XL
|  | WebKon 2017 BE | 38 | 60.4 | 60.4
|  | WebKon 2017 FE | 12 | 24 | 24
|  | Expected Features |  | 274.3
|  | WebService Connections |  | 30
|  | WebTracking ( Views) |  | 10
Common FE for VF.de/KSO
|  | Quality Measurements and Assurence ( New Relic/Application Insights) |  | 20
|  | DB Connections |  | 5
|  | Security |  | 20
|  | Exchange IDP ( WSO2 ) |  | 40
Application Server
|  | Automated Test Env. |  | 10
|  | Autoscalling Infrastructure |  | 15
|  | DB Migration |  | 15
|  | CMS Replacement ( Reddot by Hippo ) |  | 10
|  | Wiki (Documentation) |  | 20
|  | Local Development Env. |  | 15
|  | Jira -> VSTS Board |  | 10
|  | Create Build Pipelines ( CI / CD ) |  | 20
|  | Workflow |  | 34.3
2 | Technical Improvements | Features so Far - based on Jira | 148 | 425.2 | 279.2 | 77.6 | 4.1 | M
|  | Standard | 51 | 86.2 | 86.2
|  | Refactoring | 97 | 193 | 193
|  | Expected Features |  | 123
|  | Exchange SoapMock with WireMock |  | 8
|  | Quality Measurements and Assurence (Sonar/Xray) |  | 15
Soap to REST for Webservices
|  | Exchange Stripes/JSP to REST/VUE |  | 100
Microservices Creation ( Configuration Service, Contract Service)
1 | DAVIS | Features so Far - based on Jira | 3 | 0 |  | 0 | 1.2 | S
|  | Standard | 3
|  | Expected features |  | 35
|  | Async. XML to Sync. DAVIS |  | 20
|  | Integration in CEP |  | 5
|  | VIP ( SAP CRM/ISU ) to DAVIS |  | 10
1 | Mobile App | Features so Far - based on Jira | 51 | 304.2 | 104.2 | 60.4 | 6.7 | L
|  | Apps Factory | 51 | 104.2 | 104.2
|  | Expected features |  | 200
MeterReading Service
Authorisation Service ( OAUTH2/WSO2)
ConsumptionOverview Service
1 | Customer Journey | Features so Far - based on Jira | 376 | 1088.6 | 978.6 | 92.8 | 2.9 | M
|  | Customer Journey Issues | 376 | 978.6 | 978.6
|  | Expected features |  | 85
|  | AD Connection |  | 15
|  | Smart FAQ |  | 10
|  | CSO 3.0 recreation - new layout |  | 60
1 | Rebrush | Features so Far - based on Jira | 2 | 8 | 8 | 88.9 | 0.2 | S
|  | FrontEnd Rebrush | 2 | 8 | 8
|  | Expected features |  | 5 | 1
|  | FrontEnd Rebrush for this year |  | 5 | 0
1 | iService | Features So Far - based on Jira |  | 0 | 0 | 0 | 0.9 | S
|  | - |  | - | -
|  | Expected features |  | 25
|  | Mails via APIS Communication Framework |  | 25
1 | Redesign | Expected features |  | 300 |  | 0 | 10 | XL
|  | Changing layout according to requirements |  | 300
Common FE for VF.de/KSO
Note on F8: Author: APIS/DAVIS/VIP
Note on F10: Author: It can be done together with Redesign! The effort is about 2 Sprints. But rather should be covered by Redesign or together with redesign.
Note on F11: Author: Would be good to contact Bastian (15-20)
Note on F14: Author: Maybe we won't need to do it (10-40)
Note on D15: Author: Not sure how to estimate that
Note on D21: Author: Could be Technical improvenet issue
Note on F21: Author: Uncertain
Note on F23: Author: (15-20)
Note on D24: Author: Ovehead of all activities around
Note on F24: Author: 15% of the time
Note on F29: Author: We can rely on iPass initial implementation
Note on F32: Author: Big Effort - it will be ongoing in next years
Note on F33: Author: It is hard to estimate - it is a 21 processes that need to be done. Architecture need to be defined. 1 process could be delivered even in 6 Sprints.
Note on F38: Author: Rely on iPas implementation
Note on F39: Author: waiting and communication, testing time
Note on F40: Author: Assumption: model and response stays the same. If we need to also reimplement endpoints - so 60.
Note on F44: Author: We have 1 process almost ready, we need to implement 3 more, it is based on experience. (collaboration and overhead icluded)
Note on F54: Author: Hard to estimate. Need to contact T.Zachar, M. Fahnrich, how many changes can affect the processes - what is the impact ?
Note on I65: Author: Guestimation - don't know the real scope. Consulted with Marcel Fahnrich - it his estimation
Note on F67: Author: It can be done together with Redesign! The effort is about 2 Sprints. But rather should be covered by Redesign or together with redesign.

## Blad2
2 | Technical Improvements | ALL Features | 148 | 279.1039
|  | Standard | 51 | 86.125
|  | Refactoring | 97 | 192.9789
1 | DAVIS | ALL Features | 3
|  | Standard | 3
1 | Mobile App | ALL Features | 51 | 104.125
|  | Apps Factory | 51 | 104.125
1 | Customer Journey | ALL Features | 376 | 978.6301
|  | Customer Journey Issues | 376 | 978.6301
1 | Rebranding | ALL Features | 2 | 8
|  | FrontEnd Rebrush | 2 | 8
1 | iService | All Features
3 | The Rest